## PDCA
Modified Plan - Do - Check - Act (PDCA) Chart - PROJECT MANAGEMENT
Project | Build and maintain Successful Oil Analysis Program |  |  | Launch date
Team Leader |  |  |  | Location
Support |  |  |  | Project # :
PDCA creation date |  |  |  | Team Members
Program Implemntation Completed
Status | Gates | Planned | Actual | Deliverables (% completed) | Validity
No. | Plan Create the implementation plan (broad steps and individual tasks) | Completed dates (m-d-y) |  | Progress of actions | 16.67% | Act Additional actions required to reach targets | RASCI: Responsible, Accountable, Support, Consult, Inform (assign roles/responsibilities of team members for each task)
|  |  |  | Do Outline the actions necessary to complete the tasks. | Check |  | R | A | S | C | I
|  | Planned | Actual
A. | Program Implemention | 2021-09-30 |  |  | 66.67%
A.1 | Setup oil analysis database |  |  | Setup equipment lists and oil type information in myLab database | 25%
A.2 | Establish new oil reference library |  |  | Collect new oil reference samples of all oils used on site, add to library | 75%
A.3 | Sample routes or scope / frequencies / budget |  |  | Review the current oil sample schedule for equipment and components, make changes as nessessary, develop budget based on audit | 100%
A.4 | Establish freight logistics |  |  | Research and test the various freight options for samples, decide on the best process, create procedure
A.5 | Confirm warehouse inventory levels are adequate |  |  | Confirm all necessary tools (bottles, pumps, tubing, valves, etc) are stocked, review inventory requirements
A.6 | Establish program metrics that will be tracked and reported |  |  | Define metrics and targets for success
A.7 | Establish and document workflow for the oil analysis process |  |  | Map out the workflow for sample requests, collection, labelling, shipping, testing, creation of alerts, communication protocols, interpretation and decision process, validation of work orders, follow up
A.8 | Add previous oil analysis histories to myLab |  |  | Obtain historial sample data from previous lab, work with IT/Fluid Life to convert and add to myLab
A.9 | Identify and complete adequate training on lubrication and oil analysis for individuals involved with program |  |  | Develop training plan for mechanics, planners, supervisors, and reliability personnel
A.10
A.11
A.12
A.13
A.14
B. | Consistent Program Execution | 2021-09-30 |  |  | 0%
B.1 | Re-validate all aspects of oil analysis program |  |  | Examine program execution of all aspects of oil analysis program as it was originally planned | 0%
B.2
B.3
B.4
C. | Validation of Program Success | 2021-09-30 |  |  | 0%
C.1 | Identify gaps in oil analysis process |  |  | Document any and all gaps in the oil analysis process - consider doing an Oil Analysis Audit | 0%
C.2 | Identify gaps in lubrication process |  |  | Dcoument any and all gaps in the lubrication process which have been uncovered using oil analysis
C.3 | Identify gaps in maintenance process |  |  | Dcoument any and all gaps in the maintenance process which have been uncovered using oil analysis
C.6
D. | Continuous Improvement | 2021-09-30 |  |  | 0%
D.1 | Creation of projects to address program gaps |  |  | Create a series of suggested projects that will address gaps in the lubrication process | 0%
D.2 | Create Budget for 20XX oil analysis program |  |  | Create budget based on anticipated needs for 20XX and current budget
D.3 | Establish priorities and resources for lubrication and reliability projects |  |  | Establish priorities and resources needed to complete the list of projects approved for 20XX
D.4
Note on F9: Monitor status of each task - indicate % completion (0, 25, 50, 75, 100)